## Run 1 Test Plan
Run 1 Test Plan
# of Testers | Total LOE in days | Planned Start Date | Actual Start Date | Planned End Date | Actual End Date
1 | 5 | 2022-12-01 |  | 2022-12-06
Environment | Version
TEST | 1.1.2
# of TCs | To Do | Pass | Fail | In Progress | Blocked
3 | 5 | 4 | 3 | 2 | 1
# of Defects | New | Open | Fixed | Retest In Progress | Done
1 | 5 | 4 | 3 | 2 | 1
Formulas:
Planned End Date = SUM([Planned Start Date], [Total LOE in days])

## Run 1 Test Suite
TC # | TC Name | Description | Steps | Data | Expected Result | Actual Result | Comments
1 | TC_Login_ValidLogin | To verify that user is able to login when valid username and password are entered. |  |  |  | Pass
|  |  | Go to <website URL> | URL = https://www.test.com/ | Website Login page is displayed. | Pass
|  |  | Enter Username. | Username = admin | Username is entered. | Pass
|  |  | Enter Password. | Password = admin | Password is entered. | Pass
|  |  | Click Login. |  | User is logged in successfully. Homepage is displayed. | Pass
2 | TC_Login_InvalidLogin | To verify that user is not allowed to login when invalid credentials are used. |  |  |  | Pass
|  |  | Go to <website URL> | URL = https://www.test.com/ | Website Login page is displayed. | Pass
|  |  | Enter Username. | Username = admin1 | Username is entered. | Pass
|  |  | Enter Password. | Password = admin | Password is entered. | Pass
|  |  | Click Login. |  | Login page is still displayed with error message displayed: "Invalid username and password." | Pass
3 | TC_Account_CreateAccount_ValidDetails | To verify that user is able to create an account successfully when details entered are valid. |  |  |  | Fail
|  |  | Go to <website URL> | URL = https://www.test.com/ | Website Login page is displayed. | Pass
|  |  | Click Create Account link. |  | Create Account page is displayed. | Pass
|  |  | Enter First Name. | First Name = Marian | First Name is entered. | Pass
|  |  | Enter Last Name. | Last Name = Juanir | Last Name is entered. | Pass
|  |  | Enter Date of Birth. | Date of Birth = January 1, 2001 | Date of Birth is entered. | Pass
|  |  | Enter Email Address. | Email Address = admin@test.com | Email Address is entered. | Pass
|  |  | Enter Password. | Password = pa$$w0rd#01 | Password is entered. | Pass
|  |  | Enter same Password in Confirm Password. |  | Password is entered. | Pass
|  |  | Click Create button. |  | Modal alert message "User is created successfully" is displayed on top. | Pass
|  |  | Click OK. |  | Alert message is closed. Homepage is displayed. | Fail | redirected to Login page again after clicking OK in the alert message

## Run 1 Defects
Defect # | Summary | Description | Priority | Severity | Status | Assigned To | Comments
1 | Redirects to Login Page after creating new account | Environment: All browsers TEST v1.1.2.0005 Steps to reproduce: 1. In any browser, go to https://www.com. 2. Click Create Account link. 3. Supply required fields and click Create. 4. Click OK in the confirmation message. Expected Result: Homepage is displayed. Actual Result: Redirects to Login page. Workaround: User needs to login | 3 | 3 | New | Unassigned

## All Test Cases
TC # | TC Name | Description | Steps | Data | Expected Result | Actual Result | Comments
1 | TC_Login_ValidLogin | To verify that user is able to login when valid username and password are entered.
|  |  | Go to <website URL> | URL = https://www.test.com/ | Website Login page is displayed.
|  |  | Enter Username. | Username = admin | Username is entered.
|  |  | Enter Password. | Password = admin | Password is entered.
|  |  | Click Login. |  | User is logged in successfully. Homepage is displayed.
2 | TC_Login_InvalidLogin | To verify that user is not allowed to login when invalid credentials are used.
|  |  | Go to <website URL> | URL = https://www.test.com/ | Website Login page is displayed.
|  |  | Enter Username. | Username = admin1 | Username is entered.
|  |  | Enter Password. | Password = admin | Password is entered.
|  |  | Click Login. |  | Login page is still displayed with error message displayed: "Invalid username and password."
3 | TC_Account_CreateAccount_ValidDetails | To verify that user is able to create an account successfully when details entered are valid.
|  |  | Go to <website URL> | URL = https://www.test.com/ | Website Login page is displayed.
|  |  | Click Create Account link. |  | Create Account page is displayed.
|  |  | Enter First Name. | First Name = Marian | First Name is entered.
|  |  | Enter Last Name. | Last Name = Juanir | Last Name is entered.
|  |  | Enter Date of Birth. | Date of Birth = January 1, 2001 | Date of Birth is entered.
|  |  | Enter Email Address. | Email Address = admin@test.com | Email Address is entered.
|  |  | Enter Password. | Password = pa$$w0rd#01 | Password is entered.
|  |  | Enter same Password in Confirm Password. |  | Password is entered.
|  |  | Click Create button. |  | Modal alert message "User is created successfully" is displayed on top.
|  |  | Click OK. |  | Alert message is closed. Homepage is displayed.

## Defect Report Template
The following information has to be provided when reporting a failure:
Issue Summary: Issue Description: - Context of the issue if relevant - Browser, build version, environment, login used - Steps to reproduce - Expected Result - Actual Result Priority and Severity Logs and/or screenshots Workaround Assignee